## Issue
Module | Menu | Sub page / Subpage | Task Title | Training Feedbacks Details | Feed back/Issue dement work | Solved Date
ALL | All | All | File Upload size auto convert | If file upload size 5MB or 20MB etc, its auto convert 500 KB (all file size save database below 500 KB) |  | 23-09-019
All | All | All | In Select Field Upazilla Need To added metropoliton thana as a value | In Select Field Upazilla Need To add metropoliton thana as a value
All | All | All | Washing and crushing all lable change to Washing And Crushing (Industrial) union | Washing and crushing all lable change to Washing And Crushing (Industrial) Union |  | 23-09-019
Access Control | User | Add New User | If association login then user group only show Association & miller | If association login then user group only show Association & Miller
Access Control | User | Add New User | User full name bangla field replace to designation | User full name bangla field replace to designation
Profile | Millers Profile | Certificate | Need Renewal alert message | One month before need alert notification of nenewal date(if Certificate type Edible & BSTI then message show like as "if don’t nenewal then account is deactivate" ) 3 message 3 month before (blue, yello, red) | 1.update problem solve enterpreneur info 2.add multiple row and remove row button based on type of owner both in create and edit enterpreneur info and update enterpreneur info 3.add multiple row and remove row problem solve,new dynamic row create select option prblem solve in enterpreneur info and insert new data when update enterpreneur info | 29-09-019 20-10-2019 24/10/2019
Profile | Millers Profile | Certificate | Certificate type VAT, BIDA is life time | If Certificate type life time then renewal date don’t mandatory | Add a new crud for mappin between certificate and issuer | 28-0-019
Profile | Millers Profile | Certificate | Certificate type Industrial, Edible & BSTI must be | If Certificate type Industrial, Edible & BSTI then with out this Certificate millers don't enrollment in this system & already enrollment millers Certificate type Industrial, Edible & BSTI if period of validity expired then one week later millers auto convert from active to inactive & dont login in this system. Afer then association will edit the renewal date & millers again active & access this system (In This validatioin Industrial, not needed) | work on cetificate info for some validation (30-09-019) | 01-09-019
Profile | Millers Profile | Certificate | Certificate period of validity expired action needed | If Certificate period of validity expired then row colour will show red for all Certificate | required field validation for certificate(02-10-2019) 1.multiple add row require problem solve 2.multiple add row select problem solve 3.create new certificate information store issue 4.certificate information button anable or disable problem solve | 16/10/2019 19/10/2019 23/10/2019
Profile | Millers Profile | Certificate | Multiple Certificate save error | When attached multiple certificate at a time & submit show error
Profile | Millers Profile | Certificate | Type of Certificate & Issure Name incorporate in same from as a map | In Certificate setup add Issure name provision and when select certificate typr issure na,me to auto seslect. |  | 2019-09-01
Profile | Millers Profile | Certificate | Need a district field(select field) after issure name | Need a district field(select field) after issure name in Certificate from (millers, Association)
Profile | Millers Profile | Mill information | Need attached field as a millers logo in Mill Information | Need attached field as a millers logo (what is when login miller) | 1.remove drop down and set text field with edit data when miller information update | 20/10/2019
Profile | Millers Profile | Edit millers profile | Need approval system when millers profile edited by himself | When millers profile edited by himself then need approval form association before finilized it (also approved comment needed) | 1.enterprenure information add remove row button problem solve 2.miller's data insert into temporary table for approval 3.miller owner type wise entrepreneur information add and remove button problem solve 4.certificate information create update required validation problem solve 5.certificate information create update button enable disable problem solve 6. miller certificate information give validation 7.miller certificate information remove button click to remove data from database | 26/10/2019 27/10/2019 28/10/2019
Profile | Millers Profile | Employee | Total number of employee need to auto calculate | When full time employee + part time employee = total number of employee auto set & part time & full time could be null | 1.add input field require validation 2. employee information issue solve when create | 19/10/2019 21/10/2019 22/10/2019
Profile | Millers Profile | Mill information | Capacity field not select box its text field () | Change to Capacity field text field not select box & level change to "Capacity(TPA)"
Profile | Millers Profile | Mill information | If Type Of Owner is single then Entrepreneur info "+" button disable | If Type Of Owner is single then Entrepreneur info "+" button disable when back then Entrepreneur type don’t found |  | 2019-09-01
Profile | Supplier profile | Add new | In supplier profile trade "licence no" is not mandatory field phone number is mandatory field | In supplier profile trade "licence no" is not mandatory field. Phone number is mandatory field
Profile | Seller Profile | Add new | Need to set Seller Type by default wholesaler | Seller Type by default whole seller
Profile | Seller Profile | Add new | Licence No. not mandatory, phone number is mandatory | Licence No. not mandatory, Phone number is mandatory |  | 26-09-019
Transaction | Chemical Purchase | Add New | By default chemical source is bscic not BSTI | Need to edit default chemical source is BSCIC not BSTI | add new query for defult value BSCIC | 24-09-019
Transaction | Crude salt Procurment | Menu & form title | Menu name & from title need to change "Crude salt purchases" from "Crude salt Procurment" | Menu name & from title need to change "Crude salt purchases" from "Crude salt Procurment" |  | 23-09-019
Transaction | Crude salt Procurment | Add new | Need transport details in Crude Salt Procurment From | Need transport details in Crude Salt Procurment From
Transaction | W & C | Menu | W & C from Loded error | Need to be solved
Transaction | Iodized | Add new | Recommended Chemical is place to Amount of Chemical field (don’t change the amount fixed) | Recommended Chemical will auot place in Amount of Chemical field
Transaction | Iodized | Add new | Iodized from title change | Iodized from title change to "Iodization" from " Iodize" |  | 23-09-019
Transaction | Iodized | Menu | Menu name change to "Iodization" from " Iodized" | Menu name change to "Iodization" from " Iodized"
Transaction | Quality Control & Testing | Add new > select batch no | Batch no auto gone when it submited for test (it will be inputed manually because of multiple test) solution by me | Batch no. auto gone when it submited for test | Add query for remove bacth id from select manue. | 25-09-019
Transaction | Quality Control & Testing | Add new >Test name | Test name by default BSTI test standard & attached file is mandatory | Test name by default BSTI test standard & attached file is mandatory |  | 23-09-019
Transaction | Sales | Add new >seller type | By default seller type need to set wholeseller | By default seller type need to set wholeseller | add a new query for wholeseller trader name by default
Transaction | Sales | Add new >Sales Calculation | Need to check sale calculation | Need to check sale calculation |  | 24-09-019
Transaction | Sales | Add new >Sales Calculation | Field level need to change | Salt Package level need to change to items name(Package)
Transaction | Sales | Add new >Sales Calculation | Need new field before Salt Package | Need a setup(millers setup) for brand neme & added this select field before salt Package field |  | 24-09-019
Transaction | Sales | Add new >Sales Calculation | Salt package field need to value 40kG to 80KG as a items type (this field need to search option) | Salt package field need to value 40kG to 80KG as a items type (this field need to search option)
Transaction | Sales | Add new >Sales Calculation | In salt type set default value iodized salt | In salt type set default value iodized salt
Transaction | Sales | Add new >Transport details | Level change for Vehicle License to Dirving licence | Level change for Vehicle License to Dirving licence
Transaction | Sales | Add new >Transport details | Level change from transport name to transport rent transport fear | Level change from transport name to transport rent
Transaction | Sales | Sales list | List view show according to last submited value | List view show according to last submited value |  | 24-09-019
Transaction | New menu needed(reconciliation) | need to discuss (stock adjustment) | need to work |  |  | 25-09-019
Dashbord |  | Stock & sales report (pi chart) | Level change to Production stock(W&C + iodized) & sales report(value must be according title) | Level change to Production stock(W&C + iodized) & sales report(value must be according title)
Dashbord | Current year production chart | Bar chart | Level should be change month wise current year production chart (value need W&C , Iodized and total needed) | Level should be change month wise current year production chart (value need W&C , Iodized and total needed)
Dashbord | Production | Table list | Level should be change to last month date wise production list(value need W&C , Iodized and total needed) | Level should be change to last month date wise production list(value need W&C , Iodized and total needed)
Dashbord | Sales | Table list | Level should be change to last mont date wise sales list(value need W&C , Iodized and total needed) | Level should be change to last mont date wise sales list(value need W&C , Iodized and total needed)
Dashbord | Sales | Pie chart | Chart title needed to last mont sales report W&C vs Iodized | Chart title needed to last mont sales report W&C vs Iodized
Dashbord | KI info Needed |  | KI last year statistics (Procurment + Used + In stock) (not last year its last 3 month) | KI last year statistics (Procurment + Used + In stock)
Report | Purchase Salt > Total Purchase stock |  | no need of date field | no need of date field
Report | Purchase Chemical> purchase |  | Miller wise & date wise chemical purchases report with total summery (above)parameters needed (date between & millers wise if null then all) (need to report print with date) | Miller wise & date wise chemical purchases report with total summery (abobe)parameters needed (date between & millers wise if null then all) (need to report print with date)
Report | Purchase Chemical> purchase stock |  | Parameter needed miller wise no date wise (only for KIO3) | Parameter needed miller wise no date wise
Report | Process>Process stock |  | Miller wise current stock(W&C (Industrial)& Iodized) | Miller wise current stock(W&C (Industrial)& Iodized)
Report | Sales > Total sales |  | Parameter Needed W&C( Industrial) & Iodized (report assending order volum wise high to low) | Parameter Needed W&C( Industrial) & Iodized
API | API |  | API need for List of millers with details | API need for List of millers with details
API | API |  | API needed time wise production summary (W&C & Iodized) | API needed time wise production summary (W&C & Iodized)
Dashbord(mobile) | Dashbord(mobile) |  | Data should be show current month wise | Data should be show current month wise
W&C(mobile) | W&C |  | Level change to production entry to production process | Level change to production entry to production process
Iodized (mobile) | Iodized |  | When select chemical type apps is stop (*) | When select chemical type apps is stop (*)